## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
01a | System selection function When you start using the system | As a system user, I want to choose which system I want to use. So that I can order food as a customer or enter the system background as a manager. | 1 | 1 | The design of an initial interface, the user according to their own needs to choose to enter different systems |  | 20/3/2020 | 3/4/2020
02a | Order ramen taste selection function to choose the ramen type | As a customer I want a clear ordering interface So that I can choose ramen according to my taste | 1 | 1 | 1. The ordering interface accurately contains various attributes of ramen for customers to choose 2.Customers can choose ramen soup 3.Customers can choose the hardness of ramen 4. Customers can choose whether to add scallions or not 5. The selected properties can be modified at any time |  | 20/3/2020 | 3/4/2020
02b | Ingredient selection function After choosing the ramen | As a customer I want to choose the ingredients So that the ramen will be more to my taste | 1 | 1 | 1.Customers can choose whether to add nori or not 2. Customers can choose whether to add chashu or not 3.Customers can choose whether to add boiled eggs or not 4. The selected ingredients can be modified at any time |  | 20/3/2020 | 3/4/2020
02c | Spiciness selection function After selecting the ingredients | As a customer I want to choose my ramen's spiciness So that the ramen will be more to my taste | 1 | 1 | 1. There are six levels of spiciness for customers to choose from 2. Use 0 to 5 to represent spiciness 3. Customers can make changes at any time |  | 20/3/2020 | 3/4/2020
02d | Adding ingredients function for extra ingredient | As a customer I want an adding ingredients function So that I can add extra ingredients | 1 | 1 | 1. The feeding interface contains four additional ingredients that can be added to ramen 2. The interface shows the price of each portion of extra food 3. You are free to increase or decrease the amount of each ingredient 4. If no requirement is added, select the quantity to be 0 |  | 20/3/2020 | 3/4/2020
03a | Dining way function | As a customer I want to explain my dining options So that the screen will show me the button to choose | 1 | 1 | 1.The repast selection includes EAT IN and TAKE AWAY |  | 20/3/2020 | 3/4/2020
04a | Direct payment function Customers can pay directly by cash or credit card | As a customer I want a feature that can choose the payment option So that I can pay for my purchase by cash or credit card | 1 | 1 | 1. The interface displays the selected goods and the corresponding amount 2. Display the total amount payable 3. Choose to pay in cash or by card 4. After payment, a bill containing information about the order will be printed, according to which the clerk will prepare the meal for the customer |  | 20/3/2020 | 3/4/2020
05a | Background management system When an administrator wants to retrieve or modify background data | As a administrator I want a background management system So that I can easily obtain the sales data or modify the goods supplied | 1 | 1 | 1. The main interface of management has two options: modify menu options and get statistics 2. Select the modify menu to enter the modify interface 3. Select the statistical information and receive the statistical report within one week in the designated mailbox 4. Return to the main management interface after each operation, and the next operation can be carried out |  | 20/3/2020 | 3/4/2020
04b | Direct payment function Customers can pay directly by cash or credit card | As a customer I want a feature that can choose the payment option So that I can pay for my purchase by cash or credit card | 2 | 2 | 1. The interface displays the selected goods and the corresponding amount 2. Display the total amount payable 3. Choose to pay in cash or by card 4. After payment, a bill containing information about the order will be printed, according to which the clerk will prepare the meal for the customer |  | 3/4/2019 | 17/4/2019
06a | Membership authentication function After choosing the dining way, customers can choose whether to be a member or not | As a VIPmember I want to have access to log in my member account, So that I can get a discount | 2 | 2 | 1. The authentication interface is for users to choose whether to be members or not 2. If it is a member, directly enter the member ID to enter the member preference interface 3. If not, you can enter the member registration interface through the registration button 4. With the member description, show the preferential policies to customers |  | 3/4/2020 | 17/4/2020
06b | Intention selection function When the customer selects NO in the identification | As a ordinary customer I want the system can inform that I am not the VIP So that I can choose to regist or skip | 2 | 2 | 1. Select “Register” to enter the “Registered function” 2. Select “Skip” to directly enter the “Direct payment function” |  | 3/4/2020 | 17/4/2020
06c | Registered function After selecting "Register" | As a ordinary customer I can sign in to become a member So thatI I can become a member and get a discount | 2 | 2 | 1. The registration interface contains the name of required items 2. Must fill in phone or email 3. You can modify the information at will before confirming it 4. After confirming the information, the verification information containing the member number will be sent to the registered mobile phone/email, and popover will remind 5. Return to the login interface after registration |  | 3/4/2020 | 17/4/2020
06d | Login function When the customer selects YES in the identification Or when the user has successfully registered | As a member I want to be able to log into my membership account So that I can view my membership information and use my membership privileges | 2 | 2 | 1. Enter the member ID to enter the member discount interface |  | 3/4/2020 | 17/4/2020
06e | Member information interface After login | As a VIP member I want to see a member information interface So that I can check the number of my virtual stamps | 2 | 2 | 1. The member discount interface displays the basic information of the member and the number of virtual stamps 2. The figure will notice you can use your virtual stamps to have a discount 3. Every ten virtual stamps can use for discount 4. If the virtual stamps number is less than 10, the UI will go to the cash payment interface |  | 3/4/2020 | 17/4/2020
04b | Virtual stamps payment function Enough coupons | As a VIP member I want to use the virtual stamps to have a discount for my order. So that I can ge lower price | 2 | 2 | 1. If discount is used, the virtual stamps will go back zero. 2. The maximum price of the Noodle order will be free. |  | 3/4/2023 | 17/4/2023
04c | Virtual stamps accumulation function After each payment | As a VIP member I want the virtual stamps to accumulate automatically after each purchase So that I can get discounts by accumulating virtual stamps in next purchace. | 2 | 2 | 1. If the payment is complete, the virtual stamps will plus one. 2. If the virtual stamps is used for discount to current payment, the virtual stamps will not accumulate this time. |  | 3/4/2024 | 17/4/2024
05d | Product sales statistics function When an administrator uses the statistics function | As a administrator I want to be able to get a clear picture of each item sold each day last week when I receive the statistics So that I can reasonably adjust the supply and price of goods | 3 | 3 | 1. Present the daily sales volume of each item in a table 2. Column items are commodity names 3. The line item is the date and shows the week at the same time 4. Items sold out that day are marked prominently |  | 17/4/2021 | 1/5/2021
05e | Spiciness statistics function When an administrator uses the statistics function | As an administrator I want when I receive the statistics, I want to be able to clearly see how customers chose different spiciness last week So that I can know more about the taste of the customers | 3 | 3 | 1. Make a list of the number of times each day each spiciness is selected 2. Column items are commodity names 3. The line item is the date and shows the week 4. The most frequently selected spiciness will be marked |  | 17/4/2022 | 1/5/2022
05b | Statistical function Select to view statistics in the management system | As a administrator I want to know the sales of our products in any time So that I can clearly know the preferences of customers and the popularity of products | 4 | 4 | 1. Display the statistical report per week (send email to mailbox) 2. Shows how many copies of each option on the menu have been sold in the past week (Monday to Sunday). 3. For the "spicy" option, highlight the most popular degree of spicy. |  | 1/5/2020 | 15/5/2020
05c | Modify menu function Select the modify menu in the admin system | As a administrator I want to adjust my menu in the back So that I can easily modify the price and supply of the goods | 4 | 4 | 1. The interface shows all goods, current prices and current stock 2. You can change the price of each item at will 3. Users can choose whether to supply the product or not. Users who do not supply the product will be reminded of "sold out" when they choose 4. Every time the customer selects supply -1, he will be reminded that the stock is sold out when the stock is 0 5. After saving, the modified menu will be timely synchronized to the user's ordering interface 6. Return to the main management interface after the operation |  | 1/5/2020 | 15/5/2020
05d | Product sales statistics function When an administrator uses the statistics function | As a administrator I want to be able to get a clear picture of each item sold each day last week when I receive the statistics So that I can reasonably adjust the supply and price of goods | 4 | 4 | 1. Present the daily sales volume of each item in a table 2. Column items are commodity names 3. The line item is the date and shows the week at the same time 4. Items sold out that day are marked prominently |  | 1/5/2020 | 15/5/2020
05e | Spiciness statistics function When an administrator uses the statistics function | As an administrator I want when I receive the statistics, I want to be able to clearly see how customers chose different spiciness last week So that I can know more about the taste of the customers | 4 | 4 | 1. Make a list of the number of times each day each spiciness is selected 2. Column items are commodity names 3. The line item is the date and shows the week 4. The most frequently selected spiciness will be marked |  | 1/5/2020 | 15/5/2020